## Slide 1
D4.2
AoS1 Innovative Solutions
LESSON 6
Project Planning
& Gantt Charts
Turning your specification into a working task list, sequencing it into a Gantt chart, and assigning individual accountability for every task.
Year 11 Applied Computing — Unit 2
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Welcome slide. This lesson is D4.2 — building on Lesson 5's specification (functional/non-functional requirements, constraints, scope) to produce a full project plan: task list, Gantt chart with dependencies and critical path, and named task ownership. FIRST HALF (devices OFF): Slides 2-9, explicit teaching. Paper notes only. SECOND HALF (from the Laptop Gate slide): students open the digital workbook and build their actual project plan across Sections 1-5. Timing guide: ~35-40 min explicit, 5 min brain break, ~55-60 min application — this is a hands-on, build-your-plan lesson, so the application half should run long. Ask students to bring their Lesson 5 workbook (specification, functional requirements) — today's task list is built directly from it.

## Slide 2
WARM-UP
The Critical Path — Making Breakfast
You need toast, tea, and a piece of fruit before you leave. Toast takes 3 minutes. Tea takes 4 minutes to steep once the kettle boils (2 min). Washing an apple takes 30 seconds. You only have one pair of hands, but some jobs don't need them the whole time.
1
List the steps
Write down every step needed to have toast, tea, and fruit ready.
2
Spot what waits
Which steps can only start once another step finishes?
3
Spot what's free
Which steps can happen at the same time as something else?
Devices OFF — sketch this individually (2 min), then compare with your group
y11-ac-u2-l6-project-planning
Mr Smith
Notes: No hints beyond the prompt — let groups work it out. Give 90 seconds individual think time, then 2 minutes group comparison. Key ideas to draw out via cold-call (don't state them yourself yet): boiling the kettle and toasting can happen at the same time (parallel); tea can't steep until the kettle has boiled (dependency); washing the apple can happen any time it's convenient (has slack). Segue: "Today you're going to do exactly this for your own project — except the steps are real tasks, and getting the order wrong costs weeks, not minutes." Timing: 4-5 min total.

## Slide 3
OBJECTIVE
Learning Objective
To be able to construct a project plan (Gantt chart) that breaks a solution into tasks, sequences them with dependencies, identifies the critical path, and assigns individual accountability — and to finalise a problem statement ready for review.
🟢 Foundation
I can list my project's major tasks and estimate a rough time allocation for each.
🟡 Developing
I can sequence tasks into a Gantt chart showing dependencies, milestones, and named owners.
🟣 Extending
I can identify my critical path and justify a contingency for its riskiest dependency.
Where this fits
Lesson 5 gave you a strengthened concept and a first-draft specification — functional requirements, non-functional requirements, constraints, and scope. Today you turn that specification into a real, buildable plan: what needs to happen, in what order, and who is doing it.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Read each criterion aloud or ask a student to read it. Quick thumb-vote on which tier is their personal goal today - no need to press for public answers. Remind students: criteria map to workbook sections - Sections 1-2 cover problem statement + task list, Section 3 is the Gantt chart build, Section 4 is critical path. Timing: 2 min.

## Slide 4
EXPLICIT
D4.2 · Why Project Plans Matter
A good idea and a good specification don't automatically turn into a finished solution. Without a shared plan for who does what, when, and in what order, groups typically discover coordination problems only once it's too late to fix them.
1
Problem & Project Plan
This one — refined problem statement, task list, and Gantt chart.
2
Preferred Design
Design ideas explored, evaluation criteria confirmed.
3
Build Substantially Complete
Proof of concept ready, before testing begins.
Each milestone exists so a group's coordination is checked before moving into a phase that depends on the last one being genuinely finished — not just because a date arrived. Today builds the plan for the first one.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: PAPER NOTES phase. Students copy the three milestones down - they'll refer back to this framing across the whole unit. Ask: "Why check coordination at these three specific points, rather than just at the very end?" (Because each phase depends on the previous one being properly finished - catching a problem early is cheaper than catching it late.) Timing: 4 min.

## Slide 5
EXPLICIT
From Specification to Task List
Your functional requirements describe what the solution must do. A task list breaks the work of building it into discrete, assignable pieces — including work that isn't a functional requirement itself.
TOO VAGUE TO SCHEDULE
"Build the app."
SCHEDULABLE TASK
"Build the check-in notification screen and connect it to the reminder trigger."
Don't forget the non-building tasks
A realistic task list usually includes: finalising the design, learning a new tool, building each major feature, integrating features together, user testing, expert review, and preparing the final submission — not just "build feature X" items.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Cold-call: ask a group to name one functional requirement from their L5 workbook, then challenge the class to turn it into a schedulable task using the template on screen. Emphasise the non-building tasks box - groups very commonly forget to schedule testing, integration and documentation time, then run out of runway for it later. Timing: 4-5 min.

## Slide 6
EXPLICIT
Estimating Time Allocation
Because your doubles run on a fixed fortnightly rhythm, the most useful unit for time allocation is which week(s) a task happens in — sized against the runway actually left before each checkpoint.
Upcoming checkpoint | What's expected by then
Preferred design milestone | Design ideas explored and a preferred design confirmed, with evaluation criteria set.
Development begins | Tools and techniques chosen; the build phase starts.
Mid-build check-in | Gantt chart revisited — task status updated, at-risk dependencies flagged.
Build-complete milestone | Proof of concept, prototype, or product substantially finished, ready for testing.
Estimate honestly, not optimistically: if every task is "1 week", that usually means integration and testing haven't been accounted for. Build in a little slack on your riskiest tasks.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Point out this is the exact table from the reference site - students should recognise it and use it to sanity-check their own duration estimates. Ask a show of hands: "Who thinks their group will need more than 2 weeks to build their core feature?" - normalise realistic estimates over optimistic ones. Timing: 4 min.

## Slide 7
EXPLICIT
Dependencies & Sequencing
Some tasks can only start once another finishes — a dependency. Others don't rely on each other at all, and can run in parallel. Spotting the difference turns a list into an actual schedule.
Back to breakfast
Boiling the kettle doesn't depend on the toaster, so they run at the same time. Buttering the toast, though, depends on the toast finishing first. Total time is set by the longest chain of steps that do depend on each other — not the sum of every step.
DEPENDENT (SEQUENTIAL)
Connecting the notification feature to the database can't start until the schema is built.
User testing can't start until a working build exists.
INDEPENDENT (PARALLEL)
Designing the colour scheme and researching a notification library can happen together.
Two members building two unconnected features.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Revisit the warm-up: ask which breakfast steps were dependent and which were parallel - map them onto this slide's two columns. Cold-call a group to name one dependency and one parallel pair from their own emerging task list. Timing: 5 min.

## Slide 8
EXPLICIT
The Critical Path
The longest chain of dependent tasks from start to finish. A delay anywhere on it delays the whole project — a delay off it usually doesn't, as long as it finishes before whatever depends on it needs it.
Wk1
Wk2
Wk3
Wk4
Wk5
Wk6
Wk7
Wk8
Wk9
Design
Colour scheme
Build core
Testing
Red = critical path (Design → Build core → Testing). Colour scheme runs in parallel with slack — it could slip a week without affecting the finish date.
Finding it: trace forward through every dependency chain, add up durations along each, and the longest total is your critical path.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Walk through the diagram: ask students to add up the duration along the Design->Build core->Testing chain (2+3+2=7 weeks) vs the Colour scheme chain (1 week, feeds into nothing further shown) to see why the first is critical. This diagram matches the one on the reference site - point students there if they want to revisit it during the application half. Timing: 5 min.

## Slide 9
EXPLICIT
Monitoring & Task Delegation
Monitoring
A Gantt chart is revisited at defined points, not written once and filed away. Your class formally revisits it at the mid-build check-in and again at the start of Term 4.
What monitoring looks like
Update task status (done / in progress / not started) and flag anything at risk of missing its date — with a reason and what the group intends to do, not just a red flag on its own.
Accountability
"The group" is not an owner. Every task needs a named person responsible — otherwise tasks quietly become no one's job until it's too late.
Owner: (blank / "everyone")
Owner: named member + backup for testing
This is also the point to be honest about skill gaps — surface them now, not mid-build.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Two-part slide: left is monitoring cadence (when the plan gets revisited), right is individual accountability (who owns each task). Cold-call: "Why might a task with no named owner be the first thing to slip?" (No one feels personally responsible for noticing it's behind.) Bridge: "Now you have everything you need - task list, time estimates, dependencies, critical path, ownership. Let's build it." Timing: 4 min. Move to brain break next.

## Slide 10
Brain Break
Stand up, stretch, and tell a neighbour one task from your own life (school or home) that you think is on today's critical path for you personally.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Short physical + verbal reset before the application half. 2 minutes. The personal critical-path question keeps the concept warm without adding new content.

## Slide 11
APPLICATION
🔓 LAPTOP GATE — Devices ON from here
Building Your Project Plan
Open the workbook. Bring your Lesson 5 specification (functional requirements, constraints, scope) and your paper notes from today's explicit teaching.
1
Problem Statement
Finalise it, checked against the criteria.
2
Task List
Break your spec into 6+ schedulable tasks.
3
Gantt Chart
Owner, weeks, dependencies, milestones.
4
Critical Path
Trace it and plan a contingency.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Circulate as groups move between workbook sections. This lesson is application-heavy by design - expect the bulk of the remaining time to be spent here. Budget roughly: 10 min Section 1, 12 min Section 2, 20-25 min Section 3 (the Gantt build is the biggest task), 10 min Section 4. Remind groups the Gantt visual in the workbook updates live as they type - a good way to sanity-check their own plan visually.

## Slide 12
APPLICATION
Finalise Your Problem Statement
📋 Open your workbook — Section 1
🟢 Foundation
Write your finalised problem statement, incorporating any peer feedback from Lesson 5.
🟡 Developing
Check it against three criteria: names a specific user group, states the problem (not the solution), and is backed by evidence.
Common failure mode
A problem statement that quietly describes the solution ("students need a reminder app") instead of the problem ("students forget equipment because they pack the night before, not the morning of") makes it harder to notice if the solution drifts away from the actual need later.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Circulate and listen for problem statements that have quietly become solution statements - redirect with 'what's the underlying problem, not what you're building for it?' Groups without new peer feedback from L5 can proceed with their existing statement, lightly re-checked against the three criteria. Timing: ~8-10 min.

## Slide 13
APPLICATION
Break Your Specification Into Tasks
📋 Open your workbook — Section 2
🟡 Developing
List at least six tasks — include design, build, AND testing work, not just features.
TEMPLATE
A task turning [functional requirement] into buildable work: name the feature, then the specific action needed to build, connect, or test it.
Watch for this
Groups often list only "build feature X" tasks and forget design, integration, testing, and submission-prep tasks — these still need to be scheduled and owned, even though they're not functional requirements themselves.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Cold-call 1-2 groups to read out one task each; ask the class whether it's specific enough to schedule (has a clear start and end point). Watch for groups pasting their functional requirements in verbatim without turning them into schedulable work - push for the actual build/test/integrate action. Timing: ~10-12 min.

## Slide 14
APPLICATION
Build Your Gantt Chart
📋 Open your workbook — Section 3
🟡 Developing
For each task: name it, assign an owner, set a start week (5–17) and duration, note dependencies, flag milestones.
Task
Owner
Start week
Duration
Depends on
Milestone?
Watch it build as you type
The workbook draws a live visual bar chart below your table as you fill it in — a quick way to sanity-check whether your plan actually makes sense before your teacher reviews it.
This is the biggest task today
Budget the largest share of your remaining time here. It's fine to revise rows as you go — a Gantt chart is a working draft today, not a finished document.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: This is the core task of the lesson - allow the most time here, roughly 20-25 minutes. Circulate checking for: vague task names, missing owners, missing dependencies (groups often only fill start/duration and skip the dependency field), and start weeks that don't leave enough room before the relevant checkpoint. Groups that finish early should move straight to Section 4 (critical path) rather than waiting.

## Slide 15
APPLICATION
Critical Path & Contingency
📋 Open your workbook — Section 4
🟡 Developing
Trace the longest dependency chain in your Gantt chart. List the tasks in order and the total duration.
🟣 Extending
Name your riskiest dependency and propose one specific, concrete contingency if it slips.
🟣 Extending
Identify a task you assumed was critical but actually has slack — explain why.
A contingency is a plan, not a hope
"We'll try to work faster" is not a contingency. "If the notification library isn't working by Week 9, we'll fall back to a simpler on-screen reminder instead of a push notification" is — it names a trigger and a concrete alternative.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Circulate checking that the critical path listed actually matches the chart built in Section 3 - a common error is naming the longest single task rather than the longest dependency chain. Push back gently on vague contingencies ("we'll manage") - ask for a specific trigger and a specific fallback. Timing: ~10 min.

## Slide 16
APPLICATION
Sign-Off Checklist
📋 Open your workbook — Section 5
Every task has a named owner — not "the group".
Dependencies are marked between tasks that genuinely rely on each other.
The critical path is identified and its total duration is realistic.
Time estimates fit within the weeks actually remaining before each checkpoint.
🟣 Extending
Which member owns updating this Gantt chart at the mid-build check-in, and how will the rest of the group hear about changes?
Once every box is genuinely ticked, flag your group to your teacher for a quick review of the plan.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: This is a genuine self-check, not a rubber stamp - remind students not to tick a box unless it's actually true of their plan. Use this as your cue to start moving between groups for quick individual sign-off conversations, prioritising groups who signal they're ready first. Timing: ~5-8 min, running in parallel with your circulation.

## Slide 17
RESPONSIVE
Quick Peer Share
Swap workbooks (or screens) with a neighbouring group for 3 minutes.
1
Check every task on their Gantt chart has a named owner — not "the group".
2
Trace their critical path yourself. Does it match what they wrote in Section 4?
3
Name one dependency you think they might have missed.
Peer feedback, not marking — fresh eyes catching a missed dependency or vague owner beats finding it after the mid-build check-in.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Set a visible 3-minute timer. Remind students feedback should be specific ('this task has no owner') not vague ('looks good'). After this: exit ticket, devices off. Timing: 5 min including swap-back.

## Slide 18
EXIT TICKET
Exit Ticket
Devices OFF — complete Section 6 from memory. No looking back.
🟢 Foundation
In your own words, what is a dependency between two tasks?
🟡 Developing
What is the critical path, and why does a delay on it affect the whole project when a delay elsewhere might not?
🟣 Extending
Why is naming an individual owner for each task better than assigning tasks to "the group" as a whole?
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Collect on paper or have students complete the digital exit ticket without scrolling back. Q11 (critical path) is the real test of today's content - listen for the idea that non-critical delays have slack, not just a repeated definition. Timing: 5 min.

## Slide 19
NEXT STEPS
Looking Ahead
D5.1 · DESIGN TOOLS & TECHNIQUES I — NEXT LESSON
Mock-ups and storyboards — groups begin generating design representations of their solution, using the task list and Gantt chart built today as the working plan behind it.
YOUR PLAN IS NOW A WORKING DOCUMENT
Keep your Gantt chart somewhere every group member can check it — it gets formally revisited at the mid-build check-in and again at the Term 4 re-orientation.
BEFORE DISMISSING
Confirm every group has: a finalised problem statement, a Gantt chart with named owners and a marked critical path, and — if not fully signed off — a plan to finish it before the next lesson.
y11-ac-u2-l6-project-planning
Mr Smith
Notes: Before dismissing: spot-check that every group has a finalised problem statement, a Gantt chart with named owners and dependencies, and a clearly marked critical path. Groups that haven't finished their plan should treat completing it as their first priority next lesson, before design work begins - the design phase depends on knowing what's actually being built and by when. No formal homework beyond finishing an incomplete plan if needed.